PRE-PROPOSAL — COTTON INCORPORATED RFP 2027

Cotton-Linter Reinforced Biodegradable Films from a
Starch–Pectin–Glycerine Formulation Platform

Dr. Amita Somya  |  Amity University Bengaluru, India

Project period: 12 months (completion by December 2027)

# 1. Work Already Carried Out in Our Laboratory

We have prepared biodegradable sheets using cornstarch, pectin, glycerine, water, and vinegar (dilute acetic acid). Films were cast from a heated starch–pectin slurry with glycerine as plasticizer and mild acid to set the network. The sheets were flexible, semi-transparent, and showed visible breakdown within about 4–8 weeks in simple soil-burial checks. The process is repeatable at bench scale.

That work is the starting point. This project adds cotton linters to the same route and adds the testing needed to judge whether the films are viable for flexible packaging.

# 2. Fit with Cotton Incorporated Priority Areas

| RFP priority area | How our project addresses it |
| --- | --- |
| 3a — Cotton-derived films / wraps as alternatives to polyethylene | Cotton linters are built into the film matrix; end use is flexible wrap/pouch-type packaging. |
| 3 — Biodegradable alternatives to single-use plastics | All major inputs are bio-based; no petroleum polymer binder. |
| 5 — Valorization of cotton processing byproducts | Cotton linters (ginning byproduct) are the main cotton input, sourced in Bengaluru. |
| 1b — Realistic biodegradation assessment (supporting) | Compost respirometry and soil/disintegration screening are included in Months 10–12. |

# 3. Objectives (12 Months)

Integrate cotton linters (10–40% dry basis) into the starch–pectin–glycerine process.

Select 2–3 formulations with acceptable flexibility, thickness, and handling.

Obtain FTIR, DSC/TGA, tensile (ASTM D882), and WVTR data against a starch-only control.

Run compost biodegradation on the lead film(s) and document results by December 2027.

## 4. Work Plan (Quarterly)

| Period | Activities | Deliverable |
| --- | --- | --- |
| Months 1–3 | Materials procurement; baseline films; cotton loading 10–30%. | Baseline + cotton films. |
| Months 4–6 | Shortlist 3 formulations; FTIR; start DSC/TGA. | FTIR/TGA report. |
| Months 7–9 | Tensile (D882), WVTR; adjust plasticizer/pectin if needed. | Mechanical/barrier data. |
| Months 10–12 | Compost test; soil checks; final report and film samples. | Biodegradation summary. |

# 5. Budget and Justification (12 Months)

The budget is built from (i) quantities needed for repeated casting and optimisation over 12 months, (ii) vendor-listed unit rates for Bengaluru suppliers where available, and (iii) quoted per-sample or per-study fees from Bengaluru analytical laboratories. GST at 18% is applied to taxable purchases and services. Staff costs follow institutional project fellowship norms. Contingency is 5% of taxable direct costs only. The project total is the sum of the line items below (no lump-sum rounding to a target figure).

| Sl. | Item | Quantity basis | Amount (incl. GST) | Justification |
| --- | --- | --- | --- | --- |
| 1 | Cotton linters (bleached / 1st cut) | 165 kg × ₹25.00/kg | ₹4,867.50 | 165 kg for ~15 casting campaigns (~10 kg each), linter grinding trials, and reserve for moisture equilibration repeats. |
| 2 | Food-grade maize starch (baseline + hybrid films) | 100 kg × ₹39.00/kg | ₹4,602.00 | 100 kg for starch control films and starch–cotton blends through optimisation (Months 1–9). |
| 3 | Pectin powder (food grade) | 18 kg × ₹1,098.00/kg | ₹23,321.52 | 18 kg: binder at 5–12% in repeated 2–3 kg batch scales across the formulation matrix. |
| 4 | Glycerine (>99%, lab / industrial grade) | 28 kg × ₹250.00/kg | ₹8,260.00 | 28 kg plasticizer for 15–20% loading trials on all active formulations. |
| 5 | Glacial acetic acid | 22 kg × ₹100.00/kg | ₹2,596.00 | 22 kg for pH control and vinegar-equivalent acidification in routine casting. |
| 6 | Food-grade vinegar, caustic soda flakes, distilled water supplements | 1 lot @ ₹22,400.00 | ₹26,432.00 | Minor reagents and repeat purchase of vinegar for pilot batches (proforma lot). |
| 7 | Borosilicate beakers, measuring cylinders, spatulas | 1 set @ ₹36,400.00 | ₹42,952.00 | Dedicated glassware for parallel casting lanes (2–3 formulations/week in active phase). |
| 8 | Teflon casting plates, levelling knives, release sheets | 1 set @ ₹22,800.00 | ₹26,904.00 | Non-stick casting surface for uniform film thickness (target 80–120 µm). |
| 9 | Filter paper, aluminium foil, HDPE bags, desiccant, lab labels | 1 lot @ ₹18,650.00 | ₹22,007.00 | Conditioning and storage of films before FTIR, tensile, and biodegradation submission. |
| 10 | Magnetic hotplate stirrer with digital temperature control | 2 unit × ₹12,850.00/unit | ₹30,326.00 | Two units so baseline and cotton formulations can run in parallel during Months 2–8. |
| 11 | Vacuum oven (25 L) for controlled drying | 1 unit × ₹89,500.00/unit | ₹105,610.00 | Stable drying after casting; department oven is shared and not always available. |
| 12 | Digital thickness gauge (0–10 mm) | 1 unit × ₹9,650.00/unit | ₹11,387.00 | Ten-point thickness per film for tensile and WVTR sample preparation. |
| 13 | FTIR — formulation fingerprinting & cotton–starch comparison | 20 sample × ₹4,500.00/sample | ₹106,200.00 | 20 spectra: 8 variants × 2 prep + 4 repeat checks after formulation lock-in. |
| 14 | DSC / TGA — thermal transitions & mass loss | 22 sample × ₹3,850.00/sample | ₹99,946.00 | 18 runs on short-listed films plus starch control and blank pans. |
| 15 | Tensile properties (ASTM D882) — 3 formulations, 5 specimens each | 1 study @ ₹168,400.00 | ₹198,712.00 | One outsourced campaign; 15 dog-bone specimens cut from cast films (quoted as package). |
| 16 | WVTR (ASTM E96 gravimetric) & moisture uptake panel | 8 sample × ₹4,650.00/sample | ₹43,896.00 | 8 film sets: 3 leads + control, duplicate conditioning at 50% and 65% RH. |
| 17 | Compost biodegradation (ISO 14855-1 / ASTM D5338) | 3 formulation @ ₹98,500.00 | ₹348,690.00 | 3 lead films; full respirometric panel (quoted range ₹90,000–₹1,00,000 per material). |
| 18 | Disintegration / soil-burial support & compost extract screening | 1 panel @ ₹52,800.00 | ₹62,304.00 | Supplementary checks aligned with RFP interest in realistic end-of-life behaviour. |
| 19 | SEM — surface morphology of film fracture (6 specimens) | 6 sample × ₹5,800.00/sample | ₹41,064.00 | 6 micrographs on lead films after tensile failure (outsourced imaging). |
| 20 | Project Research Fellow | 12 month × ₹36,000.00/month | ₹432,000.00 | Full-time bench work: casting, conditioning, sample prep, lab coordination (12 × ₹36,000; UGC JRF–aligned rate). |
| 21 | Technical Assistant | 12 month × ₹13,200.00/month | ₹158,400.00 | Weighing, drying, cleaning, sample logging, vendor/lab runs (12 × ₹13,200). |
| 22 | PI research allowance | 12 month × ₹10,800.00/month | ₹129,600.00 | Supervision, data review, report writing (12 × ₹10,800). |
| 23 | Domestic travel & sample logistics (Bengaluru vendors / testing labs) | 9 trip × ₹6,350.00/trip | ₹57,150.00 | 9 trips for procurement, sample handover to Dextrose/Greenlink/Nanowatts, and vendor follow-up. |
| 24 | Contingency | 5% of taxable direct cost (₹1,025,489.00 excl. GST) | ₹60,503.85 | Price escalation, extra casting batches, or repeat of 2–3 failed FTIR/tensile specimens. |
|  | Total estimated project cost |  | ₹20,47,730.87 | Sum of lines 1–24 |

## 5.1 Summary by Category

| Category | Amount | Share |
| --- | --- | --- |
| Raw materials | ₹70,079.02 | 3.4% |
| Consumables | ₹91,863.00 | 4.5% |
| Equipment | ₹147,323.00 | 7.2% |
| Testing & analysis | ₹900,812.00 | 44.0% |
| Manpower | ₹720,000.00 | 35.2% |
| Travel & logistics | ₹57,150.00 | 2.8% |
| Contingency | ₹60,503.85 | 3.0% |
| Total | ₹2,047,730.87 | 100% |

## 5.2 Vendors (Bengaluru / Karnataka)

| Item | Vendor | Location | Allocation |
| --- | --- | --- | --- |
| Cotton linters (bleached / 1st cut) | Vicram Yarns And Fibers | Uttrahalli, Bengaluru 560061 | ₹4,867.50 |
| Food-grade maize starch (baseline + hybrid | Well Thought Chemicals | Peenya, Bengaluru 560058 | ₹4,602.00 |
| Pectin powder (food grade) | Amit Hydrocolloids (via Bengal | Mumbai supply to Bengaluru | ₹23,321.52 |
| Glycerine (>99%, lab / industrial grade) | Paxal Chemical Industry Pvt. L | Sheshadripuram, Bengaluru 560020 | ₹8,260.00 |
| Glacial acetic acid | Miracle Ingredients LLP | Pantharapalya, Bengaluru 560039 | ₹2,596.00 |
| Food-grade vinegar, caustic soda flakes, d | Well Thought Chemicals; local | Bengaluru | ₹26,432.00 |
| Borosilicate beakers, measuring cylinders, | Nandini Marketing Company / Bh | Bengaluru | ₹42,952.00 |
| Teflon casting plates, levelling knives, r | Bharat Scientific World | Bengaluru | ₹26,904.00 |
| Filter paper, aluminium foil, HDPE bags, d | Local scientific consumables d | Bengaluru | ₹22,007.00 |
| Magnetic hotplate stirrer with digital tem | Labindia Analytical Instrument | Bengaluru | ₹30,326.00 |
| Vacuum oven (25 L) for controlled drying | Regional lab equipment supplie | Bengaluru | ₹105,610.00 |
| Digital thickness gauge (0–10 mm) | Authorised Mitutoyo / Insize d | Bengaluru | ₹11,387.00 |
| FTIR — formulation fingerprinting & cotton | Dextrose Technologies Pvt. Ltd | Kengeri, Bengaluru 560060 | ₹106,200.00 |
| DSC / TGA — thermal transitions & mass los | Dextrose Technologies Pvt. Ltd | Kengeri, Bengaluru 560060 | ₹99,946.00 |
| Tensile properties (ASTM D882) — 3 formula | Dextrose Technologies Pvt. Ltd | Kengeri, Bengaluru 560060 | ₹198,712.00 |
| WVTR (ASTM E96 gravimetric) & moisture upt | Nanowatts Technologies | RMV 2nd Stage, Bengaluru 560094 | ₹43,896.00 |
| Compost biodegradation (ISO 14855-1 / ASTM | Greenlink Laboratory | Bengaluru | ₹348,690.00 |
| Disintegration / soil-burial support & com | Greenlink Laboratory | Bengaluru | ₹62,304.00 |
| SEM — surface morphology of film fracture | Dextrose Technologies Pvt. Ltd | Kengeri, Bengaluru 560060 | ₹41,064.00 |
| Project Research Fellow | Host institution | — | ₹432,000.00 |
| Technical Assistant | Host institution | — | ₹158,400.00 |
| PI research allowance | Host institution | — | ₹129,600.00 |

## 6. Expected Outputs and Applications

By December 2027: documented film recipe(s); FTIR/thermal/mechanical/WVTR dataset; compost biodegradation results; and prototype films for Cotton Incorporated review.

If mechanical strength and moisture resistance meet targets, the same film platform could support short-life flexible packaging where polyethylene is used today but composting or soil return is preferred:

Fresh produce overwrap and tray liners (e.g. cucumbers, herbs, berries) in retail and farm-gate packing.

Bread, bakery, and dry-snack overwrap where a breathable, compostable sheet replaces LDPE cling.

Garment and textile shipment bags for cotton apparel brands—cotton-linter content aligns with fibre sourcing narratives.

Protective wrap for cotton lint, yarn cones, or small textile rolls in mills and warehouses (byproduct-to-packaging loop).

Compostable mailers and pouch inserts for e-commerce parcels with low liquid exposure.

Horticulture: seedling collars, pot liners, or mulch sheets that can remain in soil at end of season.

Floral and gift overwrap for events and florists seeking plastic-free presentation.

These are illustrative end uses; final adoption would depend on tensile/WVTR data from this project and any food-contact or brand-specific certification required by the customer.